ZZSC9020 – Project Meeting 2: (Week 1 - 2nd meeting): Agenda
Project: Electricity Demand Forecasting (NSW) by Group A
Meeting Date: March 19, 2026 (Tuesday)
Time: 7:30pm – 8:30pm
Location / Platform: MS Teams Meeting
Attendees: Brendan, Daniel, Kam, Kelvin

- Week 1 first meeting minute and reporting of progress:

- Assessment 1B – Software Agreement (due March 24, 2025)

- Assessment 1A – finalization of project plan (due March 24, 2025)

- Discussion of forecasting horizon (put in item 2 below)

- Progress of literature review

2. Decision on forecasting horizon

3. Change in Timeline and Milestones (if any)

4. Action Items and Next Steps

5. Next Meeting date and time

ZZSC9020 – Project Meeting 2: (Week 1 - 2nd meeting): Minutes
Project: Electricity Demand Forecasting (NSW) by Group A
Meeting Date: March 19, 2026 (Tuesday)
Time: 7:30pm – 8:30pm
Location / Platform: MS Teams Meeting
Attendees: Brendan, Daniel, Kam, Kelvin

- Week 1 first meeting minute and reporting of progress:

- Assessment 1B – Software Agreement (due March 24, 2025)

|  | Justification |
| --- | --- |
| - Meeting Software – MS Teams | - Multifunction (chat, video, file sharing with University account) for efficient coordination and communication; - Can schedule meeting and record meeting, with live caption; - Compatible with University OneDrive. |
| - Collaboration Tools – GitHub | - With version control, - Collaborative development through branches and pull requests, avoid conflicts, - With tracking and project management features |
| - Data Analysis Software – Python | - Various choices of useful libraries (Pandas, NumPy, Scikit-learn, PyTorch etc), - Suitable for coding statistical models and machine learning models, - Rich resources in Python available in GitHub |
| - Reproducible Report Writing – Jupyter Notebook + MS Word | - Jupyter Notebooks allows integration of codes, outputs, explanations in a reader-friendly format, - Microsoft word provides flexibility for academic report writing |
| - Oral Presentation Software – Powerpoint + Recording Software | - PowerPoint enables clear visual communication of key findings, - Recording software enable asynchronous presentation delivery and teammates individual part can be edited easily into one single video, - Allows rehearsal, re-take, correction, refinement with flexibility. |
| - Additional Software |  |

- Assessment 1A – finalization of project plan (due March 24, 2025):

ongoing refinement (to be completed before due date March 24, 2026)

- Progress of literature review – Partially completed.  As this is part of the project plan, it is to be completed together with Assessment 1A.

- Decision on forecasting horizon

- Acknowledged as an important factor affecting:

  - Model selection

  - Usefulness of seasonal models

- No final decision made → to be revisited after literature review during the coming week.

- Kelvin found 2-3 papers with the test structure:

|  | Horizon 1 2-3 days | Horizon 2 around 10 days | Horizon 3 30-40 days |
| --- | --- | --- | --- |
| Model 1 RMSE Model 1 MAE | …… | …… | …… |
| Model 2 RMSE Model 2 MAE | …… | …… | …… |
| Model 3 RMSE Model 3 MAE | …… | …… | …… |
| Model 4 RMSE Model 4 MAE | …… | …… | …… |

- Modelling Approach Discussion

- Discussion on whether simple polynomial regression could be sufficient for time series forecasting.

- Consideration that:

  - Polynomial regression is a basic benchmark model.

  - It may reduce the need for more complex models like SARIMAX.

- SARIMAX was previously selected:

  - Advantage: captures seasonality

  - Concern: may not be necessary for short forecasting horizons

- Decision:

  - Review relevant research papers to confirm modelling choices before finalising.

- Task Allocation

- Literature Review

  - Brendan: condense and merge all literature review sections

- Introduction

  - Kelvin: draft initial version

  - Brendan: may refine / co-develop

  - Kam: available to assist

- Methodology

  - To be reviewed:

    - Ensure alignment with project plan

    - Adjust based on modelling decisions

- Coordination & Communication

- Kelvin to:

  - Share research papers with team

  - Share updated documents (agenda, tools, schedule)

- Team to continue discussions via Teams messages

- No change in Timeline and Milestones (if any)

| Week | Activities | Milestone |
| --- | --- | --- |
| Week 1 | - Form project team, - Discuss project scope and research question, - Conduct preliminary literature review, - Finalize project plan, - Confirm approaches, dataset and variables | Project plan finalized |
| Week 2 | - Data cleaning, - Preprocessing, - Exploratory data analysis, - Prepare implementation checklist | Implementation checklist prepared |
| Week 3 | - Implement and evaluate SARIMAX baseline model - Implement LSTM model and tune hyperparameters - Implement PatchTST model and draft comparison of model performance - Prepare individual reflection portfolio | 1. Model set up with results 2. Individual reflection portfolio completed |
| Week 4 |  |  |
| Week 5 | - Conduct forecasting experiments, - Draft report, and - Prepare presentation | Results and implications agreed |
| Week 6 | Finalize report and prepare presentation | Report finalized |
| Week 7 | Finalize video presentation | Videos finalized |

7. Action Items & Next Steps

Brendan and Daniel: 	Review papers on polynomial regression vs time series models

All:

- Finalize forecasting horizon (e.g. 2 days to 30 days according to some papers?)

- Preliminary model study (SARIMAX vs LSTM vs Transformer)

- Complete introduction, consolidated literature review, methodology of project plan.

8. Next Meeting date and time

Meeting Date (internal): 		March 27, 2026 (Friday) starts 7:30pm MS Teams

Meeting Date (with lecturers):	TBC