ZZSC9020 – Week 1 Project Meeting Agenda (with Wei Tian)
Project: Electricity Demand Forecasting (NSW) by Group A
Meeting Date: March 17, 2026
Time: 8pm – 9pm
Location / Platform: MS Teams Meeting
Attendees: Wei Tian, Brendan, Daniel, Kam, Kelvin

1. Reporting Status of Administrative Setups and GitHub Repository Setup

2. Reporting Project Scope and Research Question Agreed

3. Reporting Current Progress – Data Pre-processing and Preliminary Literature Review

4. Reporting Data and Variables we Agreed

5. Reporting Methods and Modelling Plan

6. Reporting Software Agreement

A. Group Meeting Software

B. Collaborative Work Management

C. Data Analysis Software

D. Reproducible Report Writing

E. Oral Presentation Software

F. Additional Software

7. Reporting Team Roles and Responsibilities

8. Reporting Timeline and Milestones

9. Questions:

a) can we use teams recording to present the paper?

b) can we use jupyter notebook or LaTeX for reporting writing?

10. Reporting Next Steps

ZZSC9020 – Week 1 Meeting Minutes 
Project: Electricity Demand Forecasting (NSW) by Group A
Meeting Date: March 17, 2026
Time: 8pm – 9pm
Location / Platform: MS Teams Meeting
Attendees: Wei Tian, Brendan, Daniel, Kam, Kelvin

1. Administrative Items

Communication platform agreed: MS Teams

Meeting frequency: 	At least once with group members per week + another with lecturer

Next meeting time: 	Next meeting: 7:30pm on March 19, 2026 (Thursday)

GitHub:

Repository name: capstone_project_GroupA (created)
Access granted to lecturers: ☑ Yes / ☐ No 	
Folder structure agreed: ☑ Yes / ☐ No 		(using default structure)

Commit frequency: Flexible, could be anytime we have made changes. At least once weekly.

Version control rules: Everyone should be able to just push changes

2. Project Scope and Research Question

Research problem summary: Can the PatchTST transformer model produce more accurate long-horizon forecasts of NSW electricity demand compared with SARIMAX and LSTM models?

Importance / motivation:

- Addressing the Operational Gap: Improved long-horizon forecasting allows for proactive grid management, reducing system instability and the risk of service disruptions during peak demand periods.

- Economic Impact: Enhancing predictive accuracy leads to greater generation efficiency and direct profitability for energy providers.

- Strategic Governance: Advanced forecasting supports national energy security by effectively integrating volatile renewable sources with traditional energy supplies.

Wei raised the question on how 55 day forecasting horizon was chosen.  Team will discuss this in the coming meeting and decide how to justify and/or adjust it.

3. Literature Review

Aim: using 3 different models to perform forecast and compare to the actual forecast and see if a better model can be chosen to improve forecast.

Some key papers selected and we will look at some more.

Section responsibilities:

- Classical models: 	Brendan and Daniel

- LSTM: 	Brendan and Daniel

- Transformers / PatchTST: 	Kam and Kelvin

Action this week: Review relevant key papers and prepare for literature review to support the key research question.

4. Data and Variables

Datasets confirmed:	using the 3 datasets provided from GitHub

Variables to include: Electricity demand, Temperature and Time-based features

Data cleaning responsibilities: 	Kam (already drafted in EDA)

Data pre-processing steps: 		Kam (already performed and shared in GitHub)

Data split for train/validation/test:	60/20/20

5. Methods and Modelling Plan

Models confirmed:
☑ SARIMAX – Lead: 	Brendan and Daniel
☑ LSTM – Lead: 		Brendan and Daniel
☑ PatchTST – Lead: 	Kam and Kelvin

Forecasting design: 	55-day horizon (justification to be included in literature review) 
Evaluation metrics:  RMSE and MAE (justification to be included in literature review)

Software/libraries:  Python, with libraries: pandas, statsmodels, PyTorch/TensorFlow etc

6. Assessment 1B – Software Agreement

|  | Software/Tools/Platform | Justification |
| --- | --- | --- |
| A. Meeting Software | MS Teams | (to be confirmed in March 19 meeting) |
| B. Collaboration Tools | GitHub | (to be confirmed in March 19 meeting) |
| C. Data Analysis Software | Python | (to be confirmed in March 19 meeting) |
| D. Reproducible Report Writing | Jupyter Notebook + LaTeX + Word | (to be confirmed in March 19 meeting) |
| E. Oral Presentation Software | Powerpoint + Recording Software (TBD in next meeting) | (to be confirmed in March 19 meeting) |
| F. Additional Software |  |  |

| 7. Roles and Responsibilities |  |  |
| --- | --- | --- |
| Responsibility; Skills. Brendan; Research consultant / lead Model analysis of SARIMAX + LSTM; Research experience Data analysis experience. Daniel; Presentation/Communication Lead Model analysis of SARIMAX + LSTM; Teaching experience Data analysis experience. Kam; Project Manager Presentation/Communication Lead3 Model lead of PatchTST + Comparison; Teaching experience Data analysis experience. Kelvin; Logistics coordinator Model lead of PatchTST + Comparison; Data analysis experience. |  |  |

8. Timeline and Milestones

| Week | Activities | Milestone |
| --- | --- | --- |
| Week 1 | - Form project team, - Discuss project scope and research question, - Conduct preliminary literature review, - Finalize project plan, - Confirm approaches, dataset and variables | Project plan finalized |
| Week 2 | - Data cleaning, - Preprocessing, - Exploratory data analysis, - Prepare implementation checklist | Implementation checklist prepared |
| Week 3 | - Implement and evaluate SARIMAX baseline model - Implement LSTM model and tune hyperparameters - Implement PatchTST model and draft comparison of model performance - Prepare individual reflection portfolio | 1. Model set up with results 2. Individual reflection portfolio completed |
| Week 4 |  |  |
| Week 5 | - Conduct forecasting experiments, - Draft report, and - Prepare presentation | Results and implications agreed |
| Week 6 | Finalize report and prepare presentation | Report finalized |
| Week 7 | Finalize video presentation | Videos finalized |

Internal deadlines agreed:

- deliverables to be ready and sent out before 10am on each internal meeting day on Fridays

- Week 1,2 deliverables: project plan and implementation checklist will be drafted by end of March 20, 2026 (Wed).

9. Action Items & Next Steps

Brendan: 	Conduct preliminary literature review(#)

Daniel: 		Conduct preliminary literature review(#)

Kam: 	Conduct preliminary literature review(#), finalize draft project plan according to the agreed items before lecturer review

Kelvin: 		Conduct preliminary literature review(#) + GANTT Chart + Book Lecturer Review

(#) Find a paper we think is useful, draft a brief summary of it and think about how it relates to our research question. Pull together in the next meeting to get bigger picture.

11. Next Meeting

Meeting Date (internal): 		March 19, 2026 (Thursday) starts 7:30pm MS Teams

Meeting Date (with lecturers):	Need basis, TBC

Appendix:

Draft Project Plan:

Research consultant / lead: driving research direction and scrutinize results (e.g. Train/Validate/Test split, epochs, other hyperparameters), drive direction of research report

Presentation/Communication lead: driving direction and main message of video presentation to meet the objective of delivering the message on how data science approach is applied to solve daily life problem in simple language

Logistics coordinator: Driving discussion, communicate with lecturers, etc